## Current
Date | Q | A | Done Date
2014-05-28 | Crawl service using e2c web service to update the store automatically
2014-05-28 | GridView First item can't be selected
2014-05-28 | Last page number of the book is not saved
2014-05-28 | Download book is not from smaller to bigger
2014-05-29 | Download notification has problem
2014-05-27 | Update the books using crawling service, crawl integrate with e2c using web service
2014-05-18 | iOS support
2014-05-11 | Optimize Volume/Book Storage by storing common part into volume
2014-05-18 | Search for given root category should only return items under that root category (now cross)
2014-05-24 | After seeking, stop current running tasks, and start the background downloading from seeked position
2014-05-18 | When returned from a searchByName category, should return to the list of search results when returned from a searchByName book, should return to it's parent volume. Now the logic is reversed.
2014-04-16 | show the number of books or/and volumes imported/downloaded/read
2014-05-23 | Customer Exception shown to customer, like connection refused
2014-05-14 | Export customized stuff
2014-05-08 | Display the path of the reading and support jumping to any parent folder/category
2014-05-08 | Display more pages or part (split) of the pages
2014-05-08 | Zoom in and Zoom out
2014-05-01 | Full Screen read
2014-05-14 | Read other formats
Edit Function
2014-05-05 | Grid View for pages to rearrange
2014-04-26 | Add Page/Book
2014-03-23 | move the sticker around on the page
Man-Machine Interactive
2014-03-23 | Define the answer
2014-03-22 | show the answer
2014-03-21 | auto check
2014-03-23 | AT: Check | e.g. check the biggest
2014-03-23 | AT: Lines | e.g. connect the number with the group
2014-03-23 | AT: Text | e.g. what is this?
2014-03-26 | Provide statistics for the book reading
2014-03-21 | audio for each page
2014-04-21 | File Dialog improvement 1. high light the selected file 2. file dialog remember last selection
Goal
Interactive messaging (Man-Machine)
Sharing (Collaberative Commenting Env) (Man-Man)
Generic Customized Browser for image, pdf, html, etc
Reminder mobile version

## Archive
Date | Q | A | Done Date
2014-03-09 | slow response to draw | since currently whiteboard talks to peers,so it is slow | 2014-03-18
2014-03-13 | seperate drawing panel |  | 2014-03-19
2014-03-14 | adding background image support |  | 2014-03-19
2014-03-15 | make erase stroke show background |  | 2014-03-19
2014-03-19 | manage book and page |  | 2014-03-21
2014-03-19 | pre-populate the book |  | 2014-03-21
2014-03-21 | rotate the image if necessary |  | 2014-03-22
2014-03-19 | turn pages |  | 2014-03-22
2014-03-23 | Lower Version support | SDK 11 | 2014-03-23
2014-03-21 | Support resources from external storage |  | 2014-03-21
2014-03-21 | Support resources from media storage |  | 2014-03-21
2014-03-23 | Support resources from internal storage/assets |  | 2014-03-23
2014-04-12 | Support resources from internet |  | 2014-04-12
2014-03-26 | save dialog box not needed for intentional save |  | 2014-03-27
2014-03-26 | portrait and landscape origin image erasing problem |  | 2014-03-26
2014-03-26 | icon, book-title not enough space, too small on tablet, both the reward and bookself |  | 2014-03-27
2014-03-26 | change subMode menu into radio selection |  | 2014-04-06
2014-03-26 | import/export book | xml marshalling/unmarshalling | 2014-04-12
2014-04-12 | delete book |  | 2014-04-12
2014-04-11 | Book Hierachy/Volume support | Adding Category Concept | 2014-04-15
2014-04-15 | Image Cache support |  | 2014-04-15
2014-04-08 | Add section into book | add volume and book and page | 2014-04-15
2014-04-16 | Create book from external folder and from asset |  | 2014-04-17
2014-04-16 | recursive delete volume |  | 2014-04-17
2014-04-16 | only url image use cache |  | 2014-04-17
2014-04-16 | correctly using the image factory decoder to avoid out of memory exception |  | 2014-04-17
2014-03-27 | Page turning too abrupt (using animation/curl ?) | having background and foreground images ready
2014-04-16 | import from zip file |  | 2014-04-20
2014-04-16 | put slow actions (import) into async mode and show non-blocking progress bar |  | 2014-04-20
2014-03-23 | Support resources from internet: dropbox |  | 2014-04-20
2014-04-23 | Remember the position of the grid view for us to navigate back |  | 2014-04-23
2014-04-23 | Duplicated Async task (download) |  | 2014-04-23
2014-04-24 | Able to browse while importing |  | 2014-04-26
2014-04-21 | Add package concept describing the installable unit and management around it select the packages which is updated or not installed either from internet or local disk |  | 2014-04-26
2014-04-26 | Update the notification/progress status for long task |  | 2014-04-26
2014-04-29 | Add Search Function |  | 2014-04-29
2014-04-23 | For Reading if name is empty show Id. if cover is empty show the 1st page. |  | 2014-05-01
2014-04-16 | Fast import using batch, and simplified page definition | 1. generate csv file and use batch insert 2. remove name, utime and empty data attributes 3. extract the page common url to the book | 5/3/2014 5/4/2014
2014-04-26 | Cancel the tasks when exit the current view, volume page, etc |  | 2014-05-02
2014-05-04 | The current page's shade fill is not the current page | Bug | 2014-05-04
2014-05-04 | Buffer more pages for reading in wifi mode |  | 2014-05-04
2014-05-04 | When Thumb-nail are loaded, it should be showed at the right position of the grid |  | 2014-05-04 | 22 | 2.3.4
2014-05-07 | Add Author attribute to Volume for 动漫 search |  | 2014-05-07
2014-05-08 | Optimize the persistence of pages by storing both common prefix and postfix of the url |  | 2014-05-08
2014-05-08 | Bulk loading also volumes xml |  | 2014-05-08
2014-05-08 | Optimize by only store book, if the page url has pattern and there is no write to the page |  | 2014-05-08
2014-05-10 | DM support |  | 2014-05-10
2014-05-11 | Adding page navigation for lots of items |  | 2014-05-10 | 23 | 2.3.5
2014-05-11 | Search limit bug and pagenum++ bug |  | 2014-05-11
2014-05-12 | Remember position of the scroll and search mode (cat or name) when doing navigation |  | 2014-05-12
2014-05-12 | Page to download for turning pages should have higher priority then total book downloading |  | 2014-05-12
2014-05-04 | When page is not loaded, and we are turning, the behavior is weird |  | 2014-05-13 | 24 | 2.3.6
2014-05-10 | Implement Swipe View (with following tabs: LHH, DM, Trading, Shopping) |  | 2014-05-14
2014-05-10 | Merge duplicated book |  | 2014-05-14 | 25 | 2.3.7
2014-05-14 | Add setting to change thread num |  | 2014-05-14
2014-05-08 | Display layered icon for volume/read/cached |  | 2014-05-14
2014-04-23 | Smoth Scrolling of the GridView/not setting the thumbnail to wrong imageView |  | 2014-05-14
2014-05-14 | book count should be calculated and recorded instead of calculate all the time |  | 2014-05-14
2014-05-14 | Display the number of books contained for folder |  | 2014-05-14
2014-05-11 | Optimize Book/Page Storage by storing the pages into book |  | 2014-05-16
2014-04-30 | 1st Grid View is not updated. | GridViewAdapter has bug to give me position 0 twice and 2nd time always the old wrong one |  | 26 | 2.3.8
2014-05-16 | Fix orientation |  | 2014-05-16
2014-05-16 | Using single db connection |  | 2014-05-16
2014-05-16 | Fragment and Activity might be detached |  | 2014-05-16
2014-05-16 | Get page from 1 |  | 2014-05-16 | 29 | 2.4.1
2014-05-17 | Create index on cat, pcat of book and volume |  | 2014-05-17 | 30 | 2.4.2
2014-05-17 | No option bar or menu visible for android 3.x | because the appication icon is too big | 2014-05-17 | 31 | 2.4.3
2014-05-17 | Cover page is the 1st page, can be delta=0 for pattern and 1 for page |  | 2014-05-17
2014-05-17 | Auto Calculate the total book number for each root category after importing |  | 2014-05-17 | 32 | 2.4.4
2014-05-17 | genearlly page n for page, n-1 for pattern |  | 2014-05-17 | 33 | 2.4.5
2014-05-18 | Add seek bar to seek to a specific page |  | 5/19/014
2014-05-18 | Image is too big for some small screen machine |  | 2014-05-19 | 34 | 2.4.6
2014-05-18 | cloud version. (Amazon ec2 and rds) 1. this can avoid connect to dropbox 2. this can avoid lengthy initial import |  | 2014-05-24
2014-05-24 | When press back key, using the caching not do db query or remote webservice query |  | 2014-05-24
2014-05-17 | FragmentManager.commit is called after saveInstances() | Using new support-v13 | 2014-05-20 | 35 | 2.4.7
2014-05-25 | Bugs (json, client sync) |  | 2014-05-25 | 36 | 2.4.8
2014-05-26 | order of books returned is not by name |  | 2014-05-26
2014-05-26 | navigation list: page number, no total page |  | 2014-05-27
2014-05-26 | my books |  | 2014-05-28
2014-05-27 | the async task will block other async task, so we need to cancel some in order to let higher priority task to start |  | 2014-05-28
2014-05-27 | switch to local mode has error |  | 2014-05-28
2014-05-24 | Turning page too slow |  | 2014-05-28 | 37 | 2.4.9

## Tests
ID | Conditions |  |  | Expected | Result
Save1 | Hit back button | is dirty | in one of the editing mode | Prompt to Save | Passed
Save2 | Saving an existing page |  |  | No prompt, just toast | Passed
Save3 | Save a new page |  |  | Prompt to name it | Passed
Save4 | After leaving/closing the book, when return/reopen |  |  | At the last reading page | Passed
Draw1 | 2 figure draw, clear all |  |  | Page should be empty | Passed